| UNITED NATIONS |  | BC UNEP/CHW/CLI_EWG.2/INF/13 |
| --- | --- | --- |
|  | Distr.: General 15 May 2014 English only |

Expert Working Group on Environmentally Sound Management

Second meeting

Jakarta, Indonesia, 29(31 May 2014

Item 4 of the provisional agenda(

Further development of work programme for

additional priorities and key work items

Draft work programme of the expert working group

Note by the Secretariat

1.	Decision BC-11/1 requested the expert working group on environmentally sound management to, among other things, develop a work programme for additional priorities and key work items and actions for the implementation of environmentally sound management.

2.	The draft work programme developed by the expert working group at its first meeting is contained in the annex to the present note. This information has not been formally edited by the Secretariat and is presented as received.

Annex

Format for work programme agreed to by the first meeting of the expert working group, including draft input from meeting participants

| Activity | Target stakeholder group | Output | Outcome | Timeline for implementation | Responsibility | Implementing partner | Budget | Indicators of achievement/ stakeholder’s feedback | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective / Priority area: Encouraging parties to develop and implement comprehensive strategies and legislation |
| Development of a workshop model on successful policies and legislation to implement ESM. | Parties, BCRCs Private sector, NGOs | Workshop model developed and BCRCs’ staff trained | Information exchange, awareness raising, report and materials produced, compilation of presentations made | 8 months | BCRCs | Secretariat and consultant | To be defined | Model developed and number of training sessions given |  |
| Elaborate guideline/manual on strategies and legislation: Value added? | Parties in a specific region: professionals in charge of waste management in the Ministry (better than for all countries of the world, as it will be adapted to regional realities) | Guideline/manual Basically 20-50 pages, with a lot of references (there will be more details, as the target stakeholders are specifically in charge of waste management) e-learning |  | 6 months | Secretariat, contracting a consultant, 2 -3 months |  | Depends on the region, what is already there, what is needed Contracting a consultant, 2 -3 months + translation + e-learning, 1 month | New strategies and legislation |  |
| Objective/priority area: Encouraging the private sector to implement and invest in ESM |
| Assessment of hazardous waste generation and management, including a system to maintain the information actualized | Waste management companies (Also useful for authorities) | Diagnosis Information system | Indication of what facilities are missing | 1 year + 1 year | Party (National government) |  | Depends on the country | New companies interested to invest; projects for new facilities presented |  |
| Elaboration of guidelines on policies and practices that support private sector investment. | Private Sector | Guidelines elaborated and disclosed | Increase in the compliance by the private sector on the waste related legislation; Capacity building | 30 months | Technical Expert Group | Consultant | To be defined | Number of guidelines elaborated and disclosed |  |
| Overcome barriers to encourage investment in ESM | Private sector |  |  |  |  |  |  |  |  |
| Preparation and conduct of workshops on incentives to ESM implementation by the private sector. | Parties Private Sector | Workshop on incentives to ESM implementation by the private sector; Report on private sector suggestions to ESM implementation | Convergence of private sector actions on ESM | 20 months | BCRCs | Parties – technical personal | To be defined | Number of workshops conducted; Report elaborated and disclosed |  |
| Pilot project to test the use of auditing and certification schemes for evaluation of ESM (for e-waste and used tyres) | Private sectors and certification bodies | Enterprises certified or they need more time for the evaluation assessment | Procedures of certification | One year if the enterprises has to raise non conformities | BCRC | Secretariat |  | Two enterprises going through the process |  |

____________________

# Footnotes

( UNEP/CHW/CLI_EWG.2/1.