### Annex 2

Further Process CLI	18.01.2010 pfr/er

| 19.1. End of January | Send out List of Elements for Inclusion in a Possible Way Forward (List of Elements) to CLI members for comments by end of January. |
| --- | --- |
| 1st week February | Revision of List of Elements based on comments of CLI members. |
| 2nd week February | Revised List of Elements sent out for comment by everybody Comments until end of March |
|  | Preparation of: Background document for OEWG Annexes: analyses Fleshed out List of Elements => Documents should be ready by 12. March |
| 12 March End of March | Send out documents to CLI members Comments until end of March |
|  | Revise documents based on comments from everybody on List of Elements and from CLI-members on draft OEWG documents. |
| Mid April | Mission Briefing in Geneva All documents for the CLI ready |
| May | OEWG: 10.5. Reception 11.5. lunch-side event normal agenda item “CLI”, to be discussed on Wednseday. |
| End of May | Possibilities to submit additional comments for everyody |
|  | If needed: amendments in analysis Further elaboration of way forward document. |
| Early July Mid August | Send out way forward document to CLI-members for comment until mid August |
|  | Revision of documents |
| Early September | Send out revised documents to everybody for comments until CLI |
| 20-24. Sept. | CLI 3 |