| UNITED NATIONS |  | BC UNEP/CHW/CLI_EWG.2/INF/13 |
| --- | --- | --- |
|  | Distr.: General 15 May 2014 English only |

Expert Working Group on Environmentally Sound Management

Second meeting

Jakarta, Indonesia, 29(31 May 2014

Item 4 of the provisional agenda(

Further development of work programme for

additional priorities and key work items

Draft work programme of the expert working group

Note by the Secretariat

1.	Decision BC-11/1 requested the expert working group on environmentally sound management to, among other things, develop a work programme for additional priorities and key work items and actions for the implementation of environmentally sound management.

2.	The draft work programme developed by the expert working group at its first meeting is contained in the annex to the present note. This information has not been formally edited by the Secretariat and is presented as received.

Annex

Format for work programme agreed to by the first meeting of the expert working group, including draft input from meeting participants

| Activity | Target stakeholder group | Output | Outcome | Timeline for implementation | Responsibility | Implementing partner | Budget | Indicators of achievement/ stakeholder’s feedback | Priority |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective / Priority area: How to ensure consistent interpretation of ESM |
| To reach agreement on the “core” of ESM (what ESM should consist of) | Parties | Practical summary document on ESM elements |  | Processing of short term work of EWG and drafting of proposal; if possible adoption at COP12; if not: consideration by OEWG10 | COP | EWG; SBC |  | Adoption of document by COP |  |
| Establish information to check when assessing if TBM meets ESM requirements, including identifying key elements for ESM of specific waste streams | Competent Authorities, Private Sector | Information established to support assessment that TBM meets ESM requirements, including “how to use” section which discusses sources of information Fact Sheets produced and disclosed | Illegal traffic and environmental damage prevented Better management of specific waste streams | 6-10 months | Expert Working Group, Secretariat, consultant | Consultants, competent authorities to implement | 20,000 USD | Number of Competent Authorities assessing if TBM meets ESM requirements Number of Fact Sheets produced and disclosed | High |
| Development of a national ESM standards and practices database | Parties, Private Sector | Provision of easily accessible information on national standards and guidelines on ESM via a website | Improvement of the knowledge on ESM standards and guidelines | 12 months | Secretariat | Consultants | To be defined | Database developed and implemented |  |
| Transposition of the core of ESM in a checklist, customized for legislators | Parties (legislators; policy developers) | Checklist that legislators can use when draft or reviewing their legislation, or legislative or policy framework | Evolution towards consistent interpretation of ESM in legislation worldwide Better informed decisions on TBM notifications | Pending adoption “core” Draft checklist: matter of months Consideration by OEWG10; adoption COP13 | COP, Parties | EWG; BRS |  | Contents of the checklist Number of Parties using the checklist |  |
| Transposition of the core of ESM in a checklist, customized for competent authorities dealing with PIC | Enforcement staff | Specific checklists for use when deciding on notifications for TBM | Evolution towards consistent interpretation of ESM in PIC worldwide Better informed decisions on TBM notifications | Pending adoption “core” Draft checklist: matter of months Consideration by OEWG10; adoption COP13 | COP, Parties | EWG; BRS; Private sector |  | Contents of the checklist Number of Parties using the checklist |  |
| Transposition of the core of ESM in a checklist, customized for enforcers on various levels | Enforcement staff | Depending on the precise target group (environmental inspectors; police, customs,…) specific checklists for use when performing inspections or controls on TBM | Evolution towards consistent interpretation of ESM in enforcement worldwide | Pending adoption “core” Draft checklist: matter of months Consideration by OEWG10; adoption COP13 | COP | EWG; BRS |  | Contents of the checklist Number of Parties using the checklist |  |
| Training courses and debriefing | Parties | Understanding and potential constitution of “regional playing field” | Creating conditions for ESM to become an accepted necessity and the understanding of a regional playing field being important | Depends of acceptance of parties | Secretariat assisted by some experts constituting the training team And BCRC for assessment of needs | Parties Or one of them Depending on geopolitical situation | If there is a real interest budget is for meeting room catering and teaching team travel | This can only be measured on medium term | Could be considered as high |
| Elaborate a standard workshop on ESM for authorities | Professionals working in evaluation and enforcement of projects, not necessarily the specialists on waste management | Documentation: texts, presentations, agenda, including a manual on how to present the presentations | Regional standard workshops implemented About 25 persons per workshop | 6months Or 6 + 6 months | Regional Centers (or ‘train de trainers’: first a consultant contracted by the Secretariat elaborates a general standard workshop, trains the bureaus, who then adapt and translate, if necessary, the general standard workshop in a regional standard workshop) | 1 responsible | 20,000 USD | Number of ‘regional standard workshops’ implemented by each regional center Or Number of participants Or Improvement of evaluation and monitoring of waste management installations. |  |
| Objective / Priority area: Encouraging parties to develop and implement comprehensive strategies and legislation |
| Development of a workshop model on successful policies and legislation to implement ESM. | Parties, BCRCs | Workshop model developed and BCRCs’ staff trained | Information exchange, awareness raising, report and materials produced, compilation of presentations made | 8 months | BCRCs | Secretariat and consultant | To be defined | Model developed and number of training sessions given |  |
| Elaborate guideline/manual on strategies and legislation | Parties in a specific region: professionals in charge of waste management in the Ministry (better than for all countries of the world, as it will be adapted to regional realities) | Guideline/manual Basically 20-50 pages, with a lot of references (there will be more details, as the target stakeholders are specifically in charge of waste management) e-learning |  | 6 months | Secretariat, contracting a consultant, 2 -3 months |  | Depends on the region, what is already there, what is needed Contracting a consultant, 2 -3 months + translation + e-learning, 1 month | New strategies and legislation |  |
| Preparation of a standard for workshop(s) on consistent understanding of ESM | Private sector, NGOs | Standard prepared and workshops executed | Information exchange, awareness raising, report and materials produced, compilation of presentations made | Standard preparation: 8 months Workshops conducted: 18 months | COP | Secretariat, BCRCs and to be defined |  | Number of workshops executed using standard |  |
| Conduct of workshops on successful policies and legislation to implement ESM. | Parties –policy makers and decision makers. | Workshops on successful policies and legislation to implement ESM | Awareness raising, capacity building | 18 months | BCRCs | Parties – technical personal | To be defined | Number of workshops held |  |
| Conduct of workshops on best practices and lessons learned on how to implement ESM. | Parties –policy makers and decision makers. | Workshops on successful policies and legislation to implement ESM | Awareness raising, capacity building | 18 months | BCRCs | Parties – technical personal | To be defined | Number of workshops held |  |
| Objective/priority area: Encouraging the private sector to implement and invest in ESM |
| Diagnosis of hazardous waste generation and management, including a system to maintain the information actualized | Waste management companies (Also useful for authorities) | Diagnosis Information system | Indication of what facilities are missing | 1 year + 1 year | Party (National government) |  | Depends on the country | New companies interested to invest; projects for new facilities presented |  |
| Elaboration of guidelines on policies and practices that support private sector investment. | Private Sector | Guidelines elaborated and disclosed | Increase in the compliance by the private sector on the waste related legislation; Capacity building | 30 months | Technical Expert Group | Consultant | To be defined | Number of guidelines elaborated and disclosed |  |
| Overarching exchange of needs and offers | Private sector, Parties, potential investment partners | Installment of a platform (by means of workshop (physical or e-), online application, database,…) | Start of pilot projects to install ESM capacity in countries/ regions in need of ESM |  | BCRCs | SBC; Parties; private sector representatives | To be defined | Exchange forum installed Number of pilots projects initiated Number of success stories |  |
| Training courses | Parties | Understanding and potential constitution of “regional playing field” | Definition of and explanation for understanding of pre-requisites for this to happen | Standard preparation: 8 months Travelling team | Secretariat assisted by some experts constituting the training team And BCRC for assessment of needs | Parties Or one of them Depending on geopolitical situation |  |  |  |
| Preparation of a workshop | Government agencies and representatives of the private sector | Collection of successful policies, best practices and lessons learned | Creation of incentives and encourage the private sector to invest in ESM | Until COP13 | Government agencies and representatives of the private sector | Secretariat, BCRCs, private sector |  | Number of workshops executed |  |
| Conduct of workshops on incentives to ESM implementation by the private sector. | Private Sector | Workshop on incentives to ESM implementation by the private sector; Report on private sector suggestions to ESM implementation | Convergence of private sector actions on ESM | 20 months | BCRCs | Parties – technical personal | To be defined | Number of workshops conducted; Report elaborated and disclosed |  |
| Pilot project to test the use of auditing and certification schemes for evaluation of ESM (for e-waste and used tyres) | Private sectors and certification bodies | Enterprises certified or they need more time for the evaluation assessment | Procedures of certification | One year if the enterprises has to raise non conformities | BCRC | Secretariat |  | Two enterprises going through the process |  |
| Objective/priority area: Ensuring that hazardous waste and other waste that is subject to TBM is managed in an environmentally sound manner |
| Transposition of the core of ESM in a checklist, customized for enforcers on various levels (management) | Enforcement staff | Depending on the precise target group (environmental inspectors; police,…) specific checklists for use when performing inspections or controls on permits, waste management activity, in-country transport,… | Evolution towards consistent interpretation of ESM in enforcement worldwide | Pending adoption “core” Draft checklist: matter of months Consideration by OEWG10; adoption COP13 | COP | EWG; SBC |  | Number of countries using the checklist |  |
| Assessment of existing auditing and certification schemes on ESM | Private Sector, NGOs | Develop an overview of existing auditing and certification schemes | Awareness raising and capacity building | 12 months | Technical Expert Group | Consultant | To be defined | Assessment report |  |
| Assessment of existing auditing and certification schemes to be applied for evaluation and of ESM |  | Feasibility study concerning certification schemes at global level, possible pilot projects |  |  |  |  |  | Feasibility of certifications schemes, voluntary or mandatory |  |
| Checklist testing during the implementation of pilot projects | Parties | A practical checklist is developed, revised and validated | Improvement on the TBM notification authorization process Evaluation of ESM facilities | 24 months | Parties | Secretariat, BCRCS and other experts | To be defined | Number of checklists revised and validated Practicability of a checklist |  |
| Testing of auditing and certification schemes during pilot project implementation | Private Sector and NGOs | Report on auditing and certification schemes relevance as a compliance verification tool | Knowledge development on auditing and certification schemes relevance/ contribution for ESM | 24 months | Technical Expert Group | Consultant | To be defined | Report elaborated |  |

____________________

# Footnotes

( UNEP/CHW/CLI_EWG.2/1.