Further Process of CLI

There are three documents coming out of the first meeting of the CLI:

- “Report” to Expanded Bureau;

- “List” of possible reasons for the transboundary movement of hazardous wastes where environmentally sound management cannot be ensured, to be finalized according process bellow;

- “Draft Analysis” of these reasons, to be produced in August

| 22. 06. |  | Co-chairs clean “List” up. Sent to CLI-members for comments. |  |
| --- | --- | --- | --- |
| 24. 06. |  | “Report” presented by co-chairs to Expanded Bureau. Publication of the “Report” (with Annex: Further Process), background documents, Presentation Introduction CLI, 5 Questions on Basel Website. Invitation to all interested stakeholders to comment on 5 questions by July 29. |  |
| 27. 06 |  | CLI-members submit to co-chairs: Comments on “List”. Indications which “reasons” could benefit from further analysis. |  |
| 1st week of July |  | Co-chairs revise the “List”. |  |
| 2nd week of July |  | Publication of the “List” on Basel Website. Invitation to all interested stakeholders to comment by July 29. |  |
| 29. 07. 31. 07 |  | Responses to 5 questions and comments on “List” handed in to co-chairs. Responses to 5 questions and comments on “List” forwarded to consultant. |  |
| July – Nov. |  | If needed: further analysis of specific issues by members of CLI and other interested stakeholders, Input to be sent to co-chairs ideally by end of July (can be used for “Draft Analysis”) or by end of November (as input for 2nd meeting) |  |
| August |  | Preparation of “Draft Analysis” by consultant. |  |
| 24. 08 |  | “Draft Analysis” sent to CLI-members for comments by September 05. |  |
| 05. 09 |  | Comments on “Draft Analysis” by CLI-members handed in. |  |
| . |  | Revision of the “Draft Analysis” by the consultant. |  |
| mid / end of September |  | Briefing of Missions in Geneva. Publication of the “Draft Analysis” on Basel Website. Invitation to all interested stakeholders to comment by October 25. |  |
| 25. 10. |  | Comments handed in. |  |
| November |  | Revision of “Draft Analysis” by consultant. |  |
| End of November |  | “Draft Analysis” and other background materials for 2nd meeting sent out. |  |
| January 12-15 |  | 2nd meeting of CLI in Switzerland. |  |